## Detailed Estimates
REGION II TRAUMA AND MEDICAL CENTER
Project Name: Completion of the Supply and Procurement Building including Construction of Road Pavement
Project Location: Magsaysay, Bayombong, Nueva Vizcaya
DETAILED ESTIMATES
Item No. | Description |  |  | Qty | Unit | Material Cost | Labor Cost | Equipment Cost | Estimated Direct Cost | Mark-ups (%) |  | Total Mark-up |  | VAT=5%(EDC+ | Total Indirect Cost | Total Cost | Unit Cost
[10 empty] | OCM | Profit | % | Value | OCM+Profit)
I | GENERAL REQUIREMENTS |  |  | 1 | lot
|  | (a). | Mobilization/Demobolization | 1 | lot
Temporary/Facilities, Water and Electric Consumption, Safety and Health Program
Permits/Licenses (Building Permit & DENR)
Project Billboard (64 sq.ft.)
Sub-Total
II | EARTHWORKS |  |  | 16.128 | cu.m.
|  |  | Excavation | 8.64 | cu.m.
|  |  | Structural Backfill | 6.912 | cu.m.
|  |  | Gravel Bedding (Material and Labor) | 0.576 | cu.m.
Sub-Total
III | FORMWORKS and SCAFFOLDINGS |  |  | 1 | lot
Materials:
|  |  | 1/2" thk Plywood | 42 | pcs.
|  |  | Assorted Good Lumber | 900 | bd. ft.
|  |  | Assorted Common Wire Nails | 1.5 | box
|  | Labor: |  | man | days
Project Engineer
Construction Foreman
Skilled Worker
Helper
|  | Equipment: |  | unit | days
|  |  | Rental of G.I. Pipes with Swivel Clamps | 1 | lot
Sub-Total
IV | ROAD PAVEMENT |  |  | 60 | cu.m.
Materials:
|  |  | Portland Cement | 540 | bags
|  |  | Sand, S1 | 30 | cu.m.
|  |  | Gravel, G1 | 60 | cu.m.
|  | Labor: |  | man | days
Project Engineer
Construction Foreman
Skilled Worker
Helper
|  | Equipment: |  | eqpt | days
|  |  | Concrete Mixer, 1 bagger | 1 | 5
|  |  | Concrete Vibrator | 1 | 5
Sub-Total
V | CONCRETE WORKS (column footing, column, beams , roof beams, suspended slab, gutter and parapet wall) |  |  | 69.12 | cu.m.
Materials:
|  |  | Portland Cement | 624 | bags
|  |  | Sand, S1 | 35 | cu.m.
|  |  | Gravel, G1 | 70 | cu.m.
|  |  | Water Proofing (toilet,deck, 3coats) | 18 | gal.
|  | Labor: |  | man | days
Project Engineer
Construction Foreman
Skilled Worker
Helper
|  | Equipment: |  | eqpt | days
|  |  | Concrete Mixer, 1 bagger | 1 | 7
|  |  | Concrete Vibrator | 1 | 7
Sub-Total
VI | REINFORCING STEEL BARS and STEEL DECKING |  |  | 1 | lot
Materials:
|  |  | 10mmØ RSB, 6m | 588 | pcs
|  |  | 12mmØ RSB, 6m | 531 | pcs
|  |  | 16mmØ RSB, 6m | 342 | pcs
|  |  | 20mmØ RSB, 6m | 99 | pcs
|  |  | #16 G.I. Tiewire | 5 | rolls
|  |  | Galvadeck W995 (50mm x 995mm), 1.00mm thk. | 43 | l.m.
|  | Labor: |  | man | days
Project Engineer
Construction Foreman
Skilled Worker
Helper
|  | Equipment |  | eqpt | days
|  |  | Cutting Machine/Cut-off Wheel | 1 | 12
Sub-Total
VII | MASONRY WORKS
| (a) | CHB Laying |  | 448.73 | sq.m.
Materials:
|  |  | Portland Cement | 345 | bags
|  |  | Sand, S-1 | 38 | cu.m.
|  |  | 150mm CHB | 3299 | pcs
|  |  | 125mm CHB | 2723 | pcs
|  |  | 10mmø RSB | 313 | pcs
|  |  | #16 G.I Tie Wire | 17 | kgs
|  | Labor: |  | man | days
Project Engineer
Construction Foreman
Skilled Worker / Mason
Helper
Sub-Total
| (b) | Plastering |  | 897.46 | sq.m.
Materials:
|  |  | Portland Cement | 290 | bags
|  |  | Screened Sand, S1 | 25 | cu.m
|  | Labor: |  | man | days
Project Engineer
Foreman
Skilled Worker / Mason
Helper
Sub-Total
VIII | TILE WORKS |  |  | 472.73 | sq.m.
Materials:
|  |  | 600mm x 600mm Polished Granite Tiles | 833 | pcs
|  |  | 600mm x 600mm non-Skid Granite Tiles | 263 | pcs
|  |  | 200mm x 200mm non-Skid Ceramic Floor Tiles | 300 | pcs
|  |  | 200mm x 300mm Ceramic Wall Tiles | 938 | pcs
|  |  | 300mm x 300mm Ceramic Floor Tiles | 376 | pcs
|  |  | Granite Slab, 3/4" thk | 2.34 | sq.m
|  |  | Portland Cement | 103 | bags
|  |  | Tile Adhesive | 30 | bags
|  |  | Screened Sand, S-1 | 25 | cu.m
|  |  | Tile Grout, 2kgs/bag | 25 | bags
|  | Labor: |  | man | days
Project Engineer
Construction Foreman
Skilled Worker / Tile Setter
Helper
Sub-Total
IX | CEILING WORKS (Third Floor) |  |  | 342 | sq.m.
Materials:
|  |  | 4.5mm thk Fiber Cement Board, 4ft x 8ft | 125 | pcs
|  |  | Carrying Channel 38mm x 12mm x 0.60mm, 5.0m | 70 | pcs
|  |  | Double Furring 50mm x 19mm x 0.40mm, 5.0m | 130 | pcs
|  |  | Wall Angle 25mm x 25mm x 0.40mm, 3.0m | 103 | pcs
|  |  | Connecting Clip | 493 | pcs
|  |  | Rod Suspension Hanger | 297 | sets
|  |  | #8 tox, 100/box | 16 | boxes
|  |  | 1/8" x 1/2" Blind Rivets, 1000pcs/box | 4 | boxes
|  |  | Black Screw | 4857 | pcs
|  | Labor: |  | man | days
Project Engineer
Construction Foreman
Skilled Worker / Carpenter
Helper
Sub-Total
X | METAL WORKS |  |  | 1 | lot
Materials:
Railings
|  |  | 50mm x 100mm x 2.0 Tubular Bars | 39 | pcs
|  |  | 25mm x 50mm x 1.2mm Tubular Steel | 127 | pcs
|  |  | 25mm x 25mm x 1.2mm Tubular Steel | 166 | pcs
|  |  | Flat Bar 38mm x 6.4mm, 6.0m | 69 | pcs
|  |  | 2" x 4" Wooden Handrail | 21 | lm
|  |  | Welding Electrodes, 20kgs/box | 4 | boxes
|  |  | Cutting Disc | 12 | pcs
Grills
|  |  | 25mm x 25mm x 1.2mm Tubular Steel, 6.00m | 21 | pcs.
|  |  | Square Bar 12mm x 12mm x 6.00m | 45 | pcs.
|  |  | Welding Electrodes, 20kgs/box | 2 | boxes
|  |  | Cut-off Wheel Cutting Disk | 6 | pcs
|  |  | Grinding Disc | 10 | pcs
|  |  | Red Oxide | 4 | gal
|  |  | Quick Drying Enamel | 7 | gal
|  |  | Paint Thinner | 4 | gal
|  |  | 2" Paint Brush | 5 | pcs
|  |  | heavy duty stainless hinges | 42 | pcs
|  | Labor: |  | man | days
Project Engineer
Construction Foreman
Skilled Worker / Welder
Helper
|  | Equipment |  | eqpt | days
|  |  | Welding Machine | 1
|  |  | Cutting Machine/Cut-off Wheel | 1
Sub-Total
XI | PAINTING WORKS |  |  | 1421.18 | sq.m.
Materials:
Concrete Walls, Columns, and Beams
Exterior
|  |  | Concrete Neutralizer | 2 | gal
|  |  | Acrylic Concrete Primer and Sealer | 15 | gal
|  |  | Elastomeric Putty (full) | 30 | gal
|  |  | Acrylic Odourless Elastomeric Paint | 30 | gal
Interior
|  |  | Concrete Neutralizer | 3 | gal
|  |  | Acrylic Concrete Primer and Sealer | 34 | gal
|  |  | Latex Putty (full) | 34 | gal
|  |  | Anti-Bacterial, Odourless & Stain-Resistant Paint | 43 | gal
Ceiling
|  |  | Acrylic Concrete Primer and Sealer | 18 | gal
|  |  | Latex Putty (full) | 18 | gal
|  |  | Anti-Bacterial, Odourless & Stain-Resistant Paint | 22 | gal
Metal Sun Buffer and Trellis
|  |  | Red Oxide Primer | 10 | gal
|  |  | Quick Drying Enamel | 20 | gal
|  |  | Paint Thinner | 10 | gal
Miscellaneous
|  |  | 7" Roller paint with pan | 12 | sets
|  |  | Paint Brush, 4" | 10 | pcs
|  |  | Paint Brush, 2" | 10 | pcs
|  |  | Paint Brush' 1" | 10 | pcs
|  |  | Sandpaper, #100 | 48 | ft
|  | Labor: |  | man | days
Project Engineer
Construction Foreman
Skilled Worker / Painter
Helper
Sub-Total
XII | FENESTRATION WORKS |  |  | 177.075 | sq.m.
Materials:
Doors
|  |  | 2.60m x 3.60m Roll up Door | 3 | sets
|  |  | (D-01) 2.00m x 2.10m Double Leaf Swing Hollow Core Metal door with S.S.H.D.Lever Lockset and Door Jamb, and complete accessories | 2 | sets
|  |  | (D-03) 1.20m x 2.10m Double Leaf Swing Hollow Core Wooden Door with View Window, S.S.H.D.Lever Lockset and 3" x 6" Tanguile Door Jamb, and complete accessories | 5 | sets
|  |  | (D-04) 0.80m x 2.10m Sliding Glass Door in Powder Coated Frame with Lockset and Door Jamb, and complete accessories | 2 | sets
|  |  | (D-05) 0.80m x 2.10m Swing Hollow Core Wooden Door with View Window S.S.H.D.Lever Lockset and 3" x 6" Tanguile Door Jamb, and complete accessories | 2 | sets
|  |  | (D-06) 0.80m x 2.10m Swing Hollow Core PVC Door with S.S.H.D.Lever Lockset and Door Jamb, and complete accessories | 3 | sets
Windows
|  |  | (W-01) 5.60m x 1.50m Swing and Awning Type Steel Casement Window with 1/4" THK Glass, with grills complete accessories | 5 | sets
|  |  | (W-03) 2.60m x 1.50m Swing and Awning Type Steel Casement Window with 1/4" THK Glass, with grills complete accessories | 1 | set
|  |  | (W-05) 2.40m x 1.50m Swing and Awning Type Steel Casement Window with 1/4" THK Glass, with grills complete accessories | 1 | set
|  |  | (W-06) 5.60m x 1.50m Fixed Powder Coated Window with 1/4" THK Glass, with complete accessories | 1 | set
|  |  | (W-07) 3.60m x 1.50m Fixed Powder Coated Window with Transaction Window with 1/4" THK Glass, with complete accessories | 1 | sets
|  |  | (W-08) 1.85m x 0.50m Awning Type Steel Casement Window with 1/4" THK Glass, with grills complete accessories | 3 | sets
|  |  | (W-09) 1.20m x 0.50m Awning Type Steel Casement Window with 1/4" THK Glass, with grills complete accessories | 2 | set
|  |  | (W-10) 2.40m x 1.50m Fixed Powder Coated Window with transaction window with 1/4" THK Glass, with complete accessories | 1 | set
|  |  | (W-11) 2.40m x 1.50m Fixed Powder Coated Window with 1/4" THK Glass, with complete accessories | 1 | set
|  |  | (W-12) 2.00m x 1.50m Sliding Powder Coated Window with 1/4" THK Glass, with complete accessories | 2 | set
|  |  | (W-13) 1.20m x 1.50m Sliding Powder Coated Window with 1/4" THK Glass, with complete accessories | 1 | set
|  |  | (W-14) 1.20m x 0.85m Sliding Powder Coated Window with 1/4" THK Glass, with complete accessories | 1 | set
|  |  | (Glass partition-01) 6.10m x 2.70m Fixed Powder Coated Window with 1/4" THK Glass, with complete accessories | 2 | sets
|  |  | (Glass Partition-02) 1.50m x 1.50m Fixed Powder Coated Office Table Partition with 1/4" THK Glass, with complete accessories | 20 | sets
|  | Labor: |  | man | days
Project Engineer
Construction Foreman
Skilled Worker
Helper
Sub-Total
XIII | ROOFING WORKS
| (a) | Steel Truss |  | 1 | lot
Materials:
|  |  | 2 1/2" x 2 1/2" x 1/4" L bar | 360 | pcs.
|  |  | 12mmØ round bar, Sagrod | 51 | pcs.
|  |  | 50mm x 2.0mm Flat Bar | 22 | pcs.
|  |  | 100mm x 50mm x 2mm C-Purlins | 143 | pcs.
|  |  | Chicken Wire, 27.5m/roll | 3 | rolls
|  |  | 100mm x 300mm x 10mm thk Gusset Plate | 442 | pcs.
|  |  | 300mm x 300mm x 12mm Base Plate | 11 | pcs.
|  |  | 200mm x 300mm x 12mm Base Plate | 33 | pcs.
|  |  | 20mmØ x 300mm Anchor Bolt with Knot and Washer | 264 | sets
|  |  | 200mm x 300mm x 6mm Base Plate | 24 | pcs.
|  |  | 12mmØ x 150mm Anchor Bolt with Knot and Washer | 136 | pcs.
|  |  | Welding Rod,5kgs/box | 20 | boxes
|  |  | Red Primer | 22 | gal.
|  |  | Paint Brush, 50mm | 8 | pcs.
|  | Labor: |  | man | days
Project Engineer
Construction Foreman
Skilled Worker
Helper
|  | Equipment |  | eqpt | days
|  |  | Welding Machine | 2 | 12
Sub-Total
| (b) | Roofing Sheet |  | 450 | l.m.
Materials:
|  |  | Duratherm 15mm Durarib 1000mm x 0.60mm x Longspan Prepainted Embosed PVC Back Cover | 450 | lm
|  |  | 0.6mm Pre Painted Pre Fabricated Gutter, 2.40m | 12 | pcs
|  |  | 0.6mm Pre Painted Pre Fabricated Ridge Gutter, 2.40m | 28 | pcs
|  |  | 0.6mm Pre Painted Pre Fabricated Flashing, , 2.40m | 21 | pcs
|  |  | 1/8" x 1/2" Blind Rivets | 6 | boxes
|  |  | 2 1/2" Teckscrew | 4130 | pcs
|  |  | Weatherproofing Sealant, 1.0kg | 4 | kgs
|  | Labor: |  | man | days
Project Engineer
Construction Foreman
Skilled Worker / Tinsmith
Helper
|  | Equipment |  | eqpt | days
|  |  | Electric Hand Drill | 1 | 0
Sub-Total
XIV | ELECTRICAL WORKS
| (a) | Wires |  | 1 | lot
Materials:
|  | 3.5mm² THHN Copper Wire |  | 13 | boxes
|  | 3.5 mm² TW Copper Wire (Grounding Condcutor) |  | 3 | boxes
|  | 5.5mm² THHN Copper Wire |  | 2 | boxes
|  | 5.5 mm² TW Copper Wire (Grounding Condcutor) |  | 1 | boxes
|  | 1.6mm² TF Copper Wire (FDAS) |  | 2 | boxes
|  | RG 6 Coaxial Siamese Cable with Power Cable ( CCTV ) |  | 10 | boxes
|  | Indoor UTP Cable CAT6 (voice and data) |  | 4 | boxes
Labor:
|  |  | Labor Cost | 1 | lot
Sub-Total
| (b) | Lighting Fixtures |  | 1 | lot
Materials:
|  | 12" x 24" Surface Mounted Flourescent Housing T8 Dust Proof Louver with 2-pcs. 9 Watts T8 LED Daylight Straight Fluorescent Tube |  | 47 | sets
|  | 4" Φ E27 Recessed Mounted Downlight, white with partial frosted glass cover with 5W DL LED Bulb |  | 11 | sets
|  | 4" Φ E27 Surface Mounted Downlight, white with partial frosted glass cover with 5W DL LED Bulb |  | 12 | sets
|  | 215mm Φ E27 Black outdoor Lmap Post with 7W DL LED Bulb |  | 4 | pcs.
|  | Twin Head Emergency Light , LED with 12 Volts Reacheargeable Battery |  | 38 | sets
Labor:
|  |  | Labor Cost | 1 | lot
Sub-Total
| (c) | Switches, Switch Plate and Convenience Outlets |  | 1 | lot
Materials:
|  | 1 gang single pole switch wide series |  | 4 | sets
|  | 2-gang single pole switch wide series |  | 12 | sets
|  | 3-gang single pole switch wide series |  | 3 | sets
|  | 3-Gang Three Way Switch wide series |  | 6 | sets
|  | Duplex 3-pronge universal convenience outlet with ground, 16A/230V, wdie series |  | 45 | sets
|  | 1 gang LAN Port Outlet and face plate (RJ-45) |  | 25 | sets
|  | 1 gang Telephone port Outlet and face plate (RJ-11) |  | 12 | sets
|  | 1-gang, universal convenience outlet wide series for (Exhaust Fan) |  | 1 | sets
|  | 1 Gang Universal Convenience Outlet with plate ( emergency light ) |  | 38 | sets
|  | aircon outlet wide series |  | 11 | sets
Labor:
|  |  | Labor Cost | 1 | lot
Sub-Total
| (d) | Fire Detection and Alarm System |  | 1 | lot
Materials:
|  | Photo electric Smoke Detector with base |  | 18 | pcs
|  | 6" Fire Alarm Bell |  | 2 | pcs
|  | Manual Call Point |  | 2 | pcs
Labor:
|  |  | Labor Cost | 1 | lot
Sub-Total
| (e) | Raceway |  | 1 | lot
Materials:
|  | Utility box GI deep type |  | 119 | pcs
|  | Junction box with cover, uPVC |  | 90 | pcs
|  | 10" x 10" Metal Pull Box |  | 5 | pcs
|  | 20mmØ uPVC Thick Wall |  | 310 | pcs
|  | 25mmØ uPVC Thick Wall |  | 120 | pcs
|  | 32mmØ uPVC Thick Wall |  | 32 | pcs
|  | 50mmØ uPVC Thick Wall |  | 4 | pcs
|  | 63mmØ uPVC Thick Wall |  | 3 | pcs
|  | 90mmØ uPVC Thick Wall |  | 4 | pcs
|  | 20mmØ uPVC long elbow |  | 82 | pcs
|  | 25mmØ uPVC long elbow |  | 35 | pcs
|  | 32mmØ uPVC Long Elbow |  | 10 | pcs
|  | 1/4' circular loom |  | 20 | m
Labor:
|  |  | Labor Cost | 1 | lot
Sub-Total
| (f) | Other Materials |  | 1 | lot
Materials:
|  | 250 ml.PVC Solvent |  | 9 | cans
|  | Electrical Tape |  | 15 | rolls
|  | Tie Wire |  | 3 | kgs
|  | Hack Saw Blade |  | 4 | pcs.
Labor:
|  |  | Labor Cost | 1 | lot
Sub-Total
| (g) | Close Circuit Television (CCTV) |  | 1 | lot
Materials:
|  | 8 Channels Digital Video Recorder 1080P with 3TB Hardisk |  | 1 | unit
|  | 16 Channels Digital Video Recorder 1080P with 3TB Hardisk |  | 1 | unit
|  | CCTV Camera Dome Type 1080P |  | 15 | units
|  | CCTV Camera Bullet Type 1080P |  | 9 | unit
|  | 24" HD Digital LED TV with wall bracket/HDMI Cable |  | 2 | set
|  | BNC Connectors |  | 48 | sets
|  | 4 Inches Nylon Cable Tie |  | 3 | packs
|  | Electrical Tape |  | 5 | rolls
|  | 12V DC Adaptor 2 Amp |  | 24 | pcs.
|  | 4 gang convenience outlet |  | 4 | pcs.
|  | 18AWG, 2-element royal cord |  | 5 | meters
|  | Surface Type Utility Box |  | 24 | pcs.
|  | screws and bolts |  | 1 | lot
Labor:
|  |  | Labor Cost | 1 | lot
Sub-Total
XV | INSTALLATION OF FIRE SUPPRESSION SYSTEM (INCLUDING ALL CONSUMABLES, TAPPING AND NEEDED SUPPORT) |  |  | 1 | lot
Materials:
|  |  | Fire Hose Cabinet with Complete Set (100ft) | 1 | set
|  |  | Fire Extinguisher (10 lbs ABC Dry Chemical) | 5 | pcs
|  |  | 2" diameter BI Pipes | 2 | pcs
|  |  | 1 1/2" diameter BI Pipe | 3 | pcs
|  |  | 2" diameter BI Pipes Coupling | 2 | pcs
|  |  | 2" diameter BI Pipes Elbow Threaded Type | 2 | pcs
|  |  | 1 1/2" diameter BI Pipe Elbow Threaded Type | 2 | pcs
|  |  | 2" diameter gate valve | 1 | pcs
|  |  | U-Bolt | 6 | pcs
|  |  | Red Oxide | 1 | gal
|  |  | Paint Thinner | 1 | gal
|  |  | 4" Paint Brush | 2 | pcs
|  |  | Cutting Disc | 5 | pcs
|  | Labor: |  | man | days
Project Engineer
Construction Foreman
Skilled Worker / Welder
Helper
|  | Equipment |  | eqpt | days
|  |  | Cutting Machine/Cut-off Wheel | 1 | 3
Sub-Total
XVI | PLUMBING WORKS
| (a) | Cold Water Line |  | 1 | lot
Materials:
|  |  | 32mmØ x 4.0m PPR Pipe, PN 16 | 6 | pcs
|  |  | 20mmØ x 4.0m PPR Pipe, PN 16 | 4 | pcs
|  |  | 32mmØ PPR Coupling | 6 | pcs
|  |  | 20mmØ PPR Coupling | 4 | pcs
|  |  | 32mmØ PPR Elbow 90° | 4 | pcs
|  |  | 20mmØ PPR Elbow 90° | 5 | pcs
|  |  | 20mm x 1/2"Ø PPR Elbow 90° with Female Thread | 5 | pcs
|  |  | 20mm x 1/2" x 20mmØ PPR Tee with Female Thread | 8 | pcs
|  |  | 32mmØ PPR Equal Tee 90° | 8 | pcs
|  |  | 20mmØ PPR Equal Tee 90° | 8 | pcs
|  |  | 32mmØ PPR Gate Valve | 3 | pcs
|  |  | 25mmØ PPR Gate Valve | 3 | pcs
|  |  | 32mmØ PPR Endcap | 5 | pcs
|  |  | 20mmØ PPR Endcap | 8 | pcs
|  |  | Teflon Tape | 1 | pcs
|  | Labor: |  | man | days
Project Engineer
Construction Foreman
Skilled Worker / Plumber
Helper
Sub-Total
| (b) | Sewer, Drainage Line, and Vent |  | 1 | lot
Materials:
|  |  | 110mmØ x 3.0m uPVC Sanitary Pipe, s 1000 | 32 | pcs
|  |  | 90mmØ x 3.0m uPVC Sanitary Pipe, s 1000 | 5 | pcs
|  |  | 63mmØ x 3.0m uPVC Sanitary Pipe, s 1000 | 5 | pcs
|  |  | 110mmØ Sanitary Wye | 3 | pcs
|  |  | 63mmØ Sanitary Wye | 4 | pcs
|  |  | 110 x 63mmØ Sanitary Wye | 2 | pcs
|  |  | 90 x 63mmØ Sanitary Wye | 3 | pcs
|  |  | 110mmØ Sanitary Coupling | 3 | pcs
|  |  | 90mmØ Sanitary Coupling | 2 | pcs
|  |  | 63mmØ Sanitary Coupling | 2 | pcs
|  |  | 110mmØ Sanitary Elbow 87.5° | 2 | pcs
|  |  | 90mmØ Sanitary Elbow 87.5° | 2 | pcs
|  |  | 63mmØ Sanitary Elbow 87.5° | 2 | pcs
|  |  | 110mmØ Elbow 45° | 1 | pcs
|  |  | 90mmØ Elbow 45° | 1 | pcs
|  |  | 63mmØ Elbow 45° | 1 | pcs
|  |  | 63mmØ U-Trap with Cap | 2 | pcs
|  |  | 110mmØ Sanitary Clean Out | 2 | pcs
|  |  | 63mmØ Sanitary Clean Out | 2 | pcs
|  |  | PVC Solvent, 1L | 1 | lit
|  | Labor: |  | man | days
Project Engineer
Construction Foreman
Skilled Worker / Plumber
Helper
Sub-Total
| (a) | Plumbing Fixtures |  | 1 | lot
Materials:
|  |  | Water Closet: Tank type Lever type Flush with Bidet, S/S Lavatory Mono Faucet, Tissue and Soap Holder complete fittings and accessories | 3 | sets
|  |  | Urinal with Lever Type Urinal Flush Valve, complete fittings and accessories | 2 | sets
|  |  | Wash Sink: Ga# 16 Stainless Steel 24x16x16 in. with C-spout faucet, complete accessories | 3 | sets
|  |  | Semi Pedestal Wash Basin (with fixing bolt set) | 4 | set
|  |  | Stainless Steel Wall Mounted Mono Faucet | 5 | sets
|  |  | Stainless Steel Lavatory/Kitchen Mono Faucet | 3 | sets
|  |  | 100mm x 100mm Stainless Steel Floor Drain | 5 | pcs
|  |  | Low Dome Roof Drain with Cast Iron Body, 76.2mm pipe size | 15 | sets
|  | Labor: |  | man | days
Project Engineer
Construction Foreman
Skilled Worker / Plumber
Helper
Sub-Total
GRAND TOTAL
Name of Company: __________________________________________________
Name of Representative: ____________________________________________
Signature of Representative: _________________________________________
Date: ______________________________________________________________

## Individual Program of Works
Republic of the Philippines
Center for Health Development No.2
REGION II TRAUMA AND MEDICAL CENTER
Bayombong, Nueva Vizcaya
INDIVIDUAL PROGRAM OF WORK
Project Title |  |  | Completion of the Supply and Procurement Building including Construction of Road Pavement
Location |  |  | REGION II TRAUMA AND MEDICAL CENTER
Source of Fund |  |  | Hospital Income
Appropriation |  |  | Php | 7137640.62
Proposed Budget for the Contract |  |  | Php | 7137640.62
Project Duration |  |  | 180 | Calendar Days
Project Type
Mode of Implementation |  |  | By Contract
Project Description |  |  | Construction of Procurement and Supply Building Completion Including Road Pavement with the following scope of work: General Requirements, Earthworks, Formworks and Scaffoldings, Road Pavement, Concrete Works, Reinforcing Steel Bars and Steel Decking, Masonry Works, Tile Works, Ceiling Works, Metal Works, Painting Works, Fenestration Works, Roofing Works, Electrical Works, Installation of Fire Suppression and Plumbing Works
Description for works to be done |  |  | Unit | Quantity | Unit Cost | Amount
I | GENERAL REQUIREMENTS |  | lot | 1
II | EARTHWORKS |  | lot | 16.128
III | FORMWORKS and SCAFFOLDINGS |  | lot | 1
IV | ROAD PAVEMENT |  | cu.m. | 60
V | CONCRETE WORKS (column footing, column, beams , roof beams, suspended slab, gutter and parapet wall) |  | cu.m. | 69.12
VI | REINFORCING STEEL BARS and STEEL DECKING |  | lot | 1
VII | MASONRY WORKS
| (a) | CHB Laying | sq.m. | 448.73
| (b) | Plastering | sq.m. | 897.46
VIII | TILE WORKS |  | sq.m. | 472.73
IX | CEILING WORKS (Third Floor) |  | sq.m. | 342
X | METAL WORKS |  | lot | 1
XI | PAINTING WORKS |  | sq.m. | 1421.18
XII | FENESTRATION WORKS |  | sq.m. | 177.075
XIII | ROOFING WORKS
| (a) | Steel Truss | lot | 1
| (b) | Roofing Sheet | l.m. | 450
XIV | ELECTRICAL WORKS
| (a) | Wires | lot | 1
| (b) | Lighting Fixtures | lot | 1
| (c) | Switches, Switch Plate and Convenience Outlets | lot | 1
| (d) | Fire Detection and Alarm System | lot | 1
| (e) | Raceway | lot | 1
| (f) | Other Materials | lot | 1
| (g) | Close Circuit Television (CCTV) | lot | 1
XV | INSTALLATION OF FIRE SUPPRESSION SYSTEM (INCLUDING ALL CONSUMABLES, TAPPING AND NEEDED SUPPORT) |  | lot | 1
XVI | PLUMBING WORKS
| (a) | Cold Water Line | lot | 1
| (b) | Sewer, Drainage Line, and Vent | lot | 1
| (c) | Plumbing Fixtures | lot | 1
TOTAL PROJECT COST
Name of Company: _________________________________________________
Name of Representative: ____________________________________________
Signature of Representative: _________________________________________
Date: ___________________________________________________________

## IPW 2
Republic of the Philippines
Center for Health Development No.2
REGION II TRAUMA AND MEDICAL CENTER
Bayombong, Nueva Vizcaya
INDIVIDUAL PROGRAM OF WORK
Project Title |  |  | Completion of the Supply and Procurement Building including Construction of Road Pavement
Location |  |  | REGION II TRAUMA AND MEDICAL CENTER
Source of Fund |  |  | Hospital Income
Appropriation |  |  | Php | 0
Proposed Budget for the Contract |  |  | Php | 0
Project Duration |  |  | 180 | Calendar Days
Mode of Implementation |  |  | By Contract
Project Description |  |  | Construction of Procurement and Supply Building Completion Including Road Pavement with the following scope of work: General Requirements, Earthworks, Formworks and Scaffoldings, Road Pavement, Concrete Works, Reinforcing Steel Bars and Steel Decking, Masonry Works, Tile Works, Ceiling Works, Metal Works, Painting Works, Fenestration Works, Roofing Works, Electrical Works, Installation of Fire Suppression and Plumbing Works
Description fo works to be done |  |  | % of Total | Manpower/Equipment Requirements
I | GENERAL REQUIREMENTS |  | 2.06% | Manpower
II | EARTHWORKS |  | 0.05% | (a) Project Engineer, (b) Construction Foreman, (c) Skilled Worker: Carpenter, Mason, Welder, Painter, Tile Setter, Plumber, Electrician, (d)Helper, (e) Electrical Engineer, and (f) Sanitary Enginner
III | FORMWORKS and SCAFFOLDINGS |  | 2.57%
IV | ROAD PAVEMENT |  | 3.53%
V | CONCRETE WORKS (column footing, column, beams , roof beams, suspended slab, gutter and parapet wall) |  | 4.77%
VI | REINFORCING STEEL BARS and STEEL DECKING |  | 7.9%
VII | MASONRY WORKS |  |  | Equipment
| (a) | CHB Laying | 5.09% | (a) One-Bagger Mixer, (b) Welding Machine, (c) Cutting Machine/ Cut-off Wheel, (d) Electric Hand Drill, (e) Excavator, (f) Dumptruck, (g) Plate Compactor, (h) Concrete Vibrator
| (b) | Plastering | 2.69%
VIII | TILE WORKS |  | 6.86%
IX | CEILING WORKS (Third Floor) |  | 3.24%
X | METAL WORKS |  | 5.21%
XI | PAINTING WORKS |  | 4.27%
XII | FENESTRATION WORKS |  | 12.87%
XIII | ROOFING WORKS
| (a) | Steel Truss | 15.21%
| (b) | Roofing Sheet | 8.09%
XIV | ELECTRICAL WORKS
| (a) | Wires | 3.91%
| (b) | Lighting Fixtures | 3.46%
| (c) | Switches, Switch Plate and Convenience Outlets | 0.57%
| (d) | Fire Detection and Alarm System | 0.61%
| (e) | Raceway | 1.08%
| (f) | Other Materials | 0.05%
| (g) | Close Circuit Television (CCTV) | 2.82%
XV | INSTALLATION OF FIRE SUPPRESSION SYSTEM (INCLUDING ALL CONSUMABLES, TAPPING AND NEEDED SUPPORT) |  | 0.67%
XVI | PLUMBING WORKS
| (a) | Cold Water Line | 0.32%
| (b) | Sewer, Drainage Line, and Vent | 0.55%
| (c) | Plumbing Fixtures | 1.54%
100%
Name of Company: _________________________________________________
Name of Representative: ____________________________________________
Signature of Representative: _________________________________________
Date: ___________________________________________________________

## Technical Specifications - SOW
Republic of the Philippines
Center for Health Development No.2
REGION II TRAUMA AND MEDICAL CENTER
Bayombong, Nueva Vizcaya
SCOPE OF WORKS
Project Title |  |  | Completion of the Supply and Procurement Building including Construction of Road Pavement
Location |  |  | REGION II TRAUMA AND MEDICAL CENTER
Source of Fund |  |  | Hospital Income
Appropriation |  |  | Php | 7137640.62
Proposed Budget for the Contract |  |  | Php | 7137640.62
Project Duration |  |  | 180 | Calendar Days
Mode of Implementation |  |  | By Contract
Project Description |  |  | Construction of Procurement and Supply Building Completion including Road Pavement with the following scope of work: General Requirements, Earthworks, Formworks and Scaffoldings, Road Pavement, Concrete Works, Reinforcing Steel Bars and Steel Decking, Masonry Works, Tile Works, Ceiling Works, Metal Works, Painting Works, Fenestration Works, Roofing Works, Electrical Works, Installation of Fire Suppression and Plumbing Works
Equipment Requirements: |  |  | (a) One-Bagger Mixer, (b) Welding Machine, (c) Cutting Machine/ Cut-off Wheel, (d) Electric Hand Drill,
(e) Excavator, (f) Dumptruck, (g) Plate Compactor, (h) Concrete Vibrator
Scope of Work
Item | Description of Work |  | Unit | Qty | Specification
I | GENERAL REQUIREMENTS |  | lot | 1
| • | Mobilization/Demobolization |  |  | • | Mobilization/demobilization of equipment, material, manpower and
| • | Temporary/Facilities, Water and Electric Consumption, Safety and Health Program |  |  |  | temporary facilities to the site including clearing of all waste or debris
generated during the entire construction duration.
| • | Project Billboard |  |  | • | Construction of Site Office and other temporary facilities.
| • | Furnishing of Materials, Labor, and Equipment |  |  | • | Observe the use of good source of potable water, and source of electricity
for the entire duration of the project.
[5 empty] | • | The contractor shall, at his own expense, furnish his workers with protective
equipment for eyes, face, hands and feet, lifeline, safety belt/harness, protective
shields and barriers whenever necessary by reason of the hazardous work
process or environment, chemical or radiological or other mechanical irritants
of hazards capable of causing injury or impairment in the function of any part of
the body through absorption, inhalation or physical agent
[5 empty] | • | All Personal Protective Equipment and Devices shall be in accordance with the
requirement of the Occupational Safety and Health Standards (OSHS) and should
pass the test conducted and/or standards sets by the Occupational Safety and
Health Center (OSHC).
[5 empty] | • | Billboard shall be installed prior to all items programmed in the project.
[5 empty] | • | Contents of billboard shall be as indicated under COA Circular No. 2013-004
[5 empty] | • | Billboard shall be installed in a safe & visible location near or within the
starting point of the project or as directed by the R2TMC Engineer-in-charge of
the project.
[5 empty] | • | The construction shall conform to all the requirements of the National
Building Code, Department of Health, as well as the local rules and regulations
of the Municipality of Bayombong, Nueva Vizcaya.
II | EARTHWORKS |  | lot | 1
| • | Leveling and shaping of subgrade using manual labor. |  |  | • | All excavations shall be made to grade as indicated in the drawings. Where the
| • | Compaction of subgrade using portable compactor. |  |  |  | building site is covered with any kind of fill, the excavation for footings should
| • | Furnishing of Aggregates Base Coarse, Labor and |  |  |  | be made deeper until the stratum for safe bearing capacity of the soil is reached.
|  | Equipment |  |  | • | Utilize suitable cut materials in addition to furnished materials.
| • | Placing and compacting of aggregates base coarse |  |  | • | Selected fill materials shall consist of pit run gravel, disintegrated rock, sand
|  | materials for slab on grade using portable compactor |  |  |  | and or other similar materials or as directed by the R2TMC Engineer-in-charge of
| • | Backfilling to suit subgrade level. |  |  |  | the project. The materials shall not contain more than 35% passing the
No. 200 sieve and fraction of the material passing the No. 40 sieve shall a
liquid limit not greater than 35 and plasticity index not greater than 12.
[5 empty] | • | Source of aggregates: Magat Gravel Pit or as directed by the R2TMC Engineer-in-
charge of the project.
III | FORMWORKS and SCAFFOLDINGS |  | lot | 1
| • | Furnishing of Materials and Labor |  |  | • | Forms and scaffoldings shall consist of form plywood and good lumber including
| • | Provision of Rentals of Equipments |  |  |  | common wire nails. All material shall be new and recycled materials shall not
| • | Provision of Stakes and Batterboards |  |  |  | be allowed.
[5 empty] | • | All forms for concrete works shall be properly braced or connected together
so as to maintain the correct position and shapes of the concrete members.
Forms shall be constructed sufficiently tight to prevent bulging and seepage
of water.
[5 empty] | • | Forms shall not be removed until the concrete has attained sufficient strength
to support its own weight and any loads that may be placed on it. Side forms
of beams and girders may be removed earlier than the bottom forms but
additional posts or shoring must be placed under the beams or girders until
they have attained their strength.
IV | ROAD PAVEMENT |  | cu.m. | 60
[5 empty] | • | All concrete works shall be done in accordance with the standard specifications
for the plain and reinforced concrete as adopted by the Government or as
directed by the R2TMC Engineer-in-charge of the Project.
[5 empty] | • | 40kgs/bag Portland cement shall be used for concrete.
[5 empty] | • | Concrete shall be well compacted after placing on its final position.
[5 empty] | • | Dimensions and other details shall be based on the issued plans and drawings.
[5 empty] | • | Concrete shall attain compressive strength of 3000psi at 28 days of age
otherwise specified in the plan or as directed the the R2TMC Engineer-in-charge
of the project.
[5 empty] | • | The coarse aggregates for concrete shall consist of round or crushed rock of
durable and strong qualities, or clean and hard gravel.
[5 empty] | • | Sand shall be washed river sand, well screened, clean, and free from loam, silt
and other impurities.
[5 empty] | • | Source of aggregates: Magat Gravel Pit or as directed by the R2TMC Engineer-in-
charge of the project.
[5 empty] | • | Fine and coarse aggregates shall pass 3/8" and 2" sieve respectively using
grading "A".
[5 empty] | • | Pouring of concrete for all reinforced concrete works must only be done
upon the approval and with direct supervision of the R2TMC Engineer-in-charge
of the project.
IV | CONCRETE WORKS (column footing, column, beams , roof beams, suspended slab, gutter and parapet wall) |  | cu.m. | 69.12
| • | Furnishing of Materials, Labor and Equipment. |  |  | • | All concrete works shall be done in accordance with the standard specifications
| • | Compaction of concrete using concrete vibrator, |  |  |  | for the plain and reinforced concrete as adopted by the Government or as
|  | maximum of 15 minutes interval. |  |  |  | directed by the R2TMC Engineer-in-charge of the Project.
| • | Provision of coarse aggregates and mixture of concrete. |  |  | • | 40kgs/bag Portland cement shall be used for concrete.
| • | Provision of concrete compressive test |  |  | • | Concrete shall be well compacted after placing on its final position.
| • | Provision of concrete slump test |  |  | • | Dimensions and other details shall be based on the issued plans and drawings.
[5 empty] | • | Concrete shall attain compressive strength of 3000psi at 28 days of age
otherwise specified in the plan or as directed the the R2TMC Engineer-in-charge
of the project.
[5 empty] | • | The coarse aggregates for concrete shall consist of round or crushed rock of
durable and strong qualities, or clean and hard gravel.
[5 empty] | • | Sand shall be washed river sand, well screened, clean, and free from loam, silt
and other impurities.
[5 empty] | • | Source of aggregates: Magat Gravel Pit or as directed by the R2TMC Engineer-in-
charge of the project.
[5 empty] | • | Fine and coarse aggregates shall pass 3/8" and 2" sieve respectively using
grading "A".
[5 empty] | • | Pouring of concrete for all reinforced concrete works must only be done
upon the approval and with direct supervision of the R2TMC Engineer-in-charge
of the project.
V | REINFORCING STEEL BARS and STEEL DECKING |  | lot | 1
| • | Furnishing of Materials, Labor, and Equipment |  |  | • | All steel reinforcing bars shall be done in accordance with the standard
specifications adopted by the Government or as directed by the R2TMC Engineer-
in-charge of the Project.
[5 empty] | • | All steel reinforcing bars to be used in this construction shall consist of round
deformed bars with lugs or projections on their sides to provide a greater bond
between the concrete and the steel.
[5 empty] | • | All steel reinforcing bars to be used shall be grade 33 otherwise specified in the
plan or as directed by the VHR Engineer-in-charge of the Project.
[5 empty] | • | The steel reinforcing bars indicated for footings, columns, slabs, beams,
girders and other concrete members shall conform to the number, size and
spacing as indicated in the drawings or schedule of steel reinforcements.
[5 empty] | • | Anchorage, lapping, and concrete cover for reinforced steel bars shall be under
the approval of the R2TMC Engineer-in-charge of the project.
[5 empty] | • | No metal reinforcement shall be installed in place unless it is free from rust,
scale or other coatings, which will destroy or reduce the bond with concrete.
VI | MASONRY WORKS
(a) | CHB Laying |  | sq.m. | 448.73
| • | Furnishing of Materials and Labor |  |  | • | All concrete hollow blocks shall be mechanically made.
| • | Provision of coarse aggregates and mixture of concrete. |  |  | • | All concrete hollow block walls shall be laid, and the cells filled with cement
mortar consisting of 1 part Portland cement and 3 parts of sand by volume
(1:3 mixture).
[5 empty] | • | 40kgs/bag Portland cement shall be used for masonry mortar
[5 empty] | • | All steel reinforcing bars to be used for masonry works shall be round
deformed bars, grade 33, with a maximum spacing of 0.60m on center both
ways unless otherwise specified in the plan or as directed by the VHR
Engineer-in-charge of the Project.
[5 empty] | • | Fine and coarse aggregates shall pass 3/8" and 2" sieve respectively using
grading "A".
[5 empty] | • | Provision of aircon space/hole for Airconditioning Unit with dimensions of atleast 74.0 x 66.0 x 43.0cm for 2.0HP Aircon and 53.0 x 48.0 x 36.0 cm for 1.0HP Aircon
(b) | Plastering |  | sq.m. | 897.46
| • | Furnishing of Materials and Labor |  |  | • | All cement plaster mixture for concrete hollow block wall finishes indicated in
| • | Provision of coarse aggregates and mixture of concrete. |  |  |  | the drawings shall be 1 part cement, and 2 parts screened sand by volumetric
method (1:2 mixture).
[5 empty] | • | Cement Plaster must have a minimum thickness of 16mm or otherwise as
directed by the R2TMC Engineer-in-charge of the project.
[5 empty] | • | 40kgs/bag Portland cement shall be used for masonry plaster
[5 empty] | • | Fine aggregates shall be clean, washed sharp river sand and free from dirt, clay,
organic matter or other deleterious substances.
VII | TILE WORKS |  | sq.m. | 472.73
| • | Furnishing of Materials, Labor, and Equipment |  |  | • | Tiles shall be standard grade.
[5 empty] | • | Color and pattern shall be specified in the drawings or as approved by the
R2TMC Engineer-in-charge of the Project.
[5 empty] | • | All cement mortar mixture for floor tiles indicated in the drawings shall be
1 part cement, and 2 parts screened sand by volumetric method (1:2 mixture).
[5 empty] | • | 40kgs/bag Portland cement shall be used for mortar of floor tiles and
25kgs/bag Tile Adhesive for wall tiles.
VIII | CEILING WORKS (Third Floor) |  | sq.m. | 342
| • | Furnishing of Materials, Labor, and Equipment |  |  | • | Ceiling Boards shall be 4.5mm. thick cement fiber board, 0.4 thick double
| • | Provision of Light Metal Framing System Installation |  |  |  | metal furring otherwise specified in the plan and/or drawing.
[5 empty] | • | Perimeter Angle or Perimeter Channel is fixed to the walls around the edge of
the room providing a location for the Ceiling Furring Channel. Primary 1.0mm
thick Channel is suspended at a maximum of 1200mm centres using
Adjustable Rod Sets otherwise specified in the plan or as directed by the
R2TMC Engineer-in-charge of the project.
IX | METAL WORKS |  | lot | 1
| • | Furnishing of Materials, Labor, and Equipment |  |  | • | Structural steel shall conform to American Society of Testing Materials (ASTM)
A-36, with Fy of 248 Mpa. Electrodes for welding shall conform to the latest
code requirements of the American Welding Society (AWS).
[5 empty] | • | Surfaces to be welded shall be free from loose scale, slag, rust, grease, paint
and any other foreign material. All butt welds shall be full penetration welds.
[5 empty] | • | No metal shall be installed in place unless it is free from rust, scale or other
coatings, which will destroy or reduce the bond with concrete.
X | PAINTING WORKS |  | sq.m. | 1421.18
| • | Furnishing of Materials, Labor, and Equipment |  |  | • | Surfaces must be clean and free from dirt, oil, grease, dust and any other
impurities that will affect the quality of the paint.
[5 empty] | • | Concrete neutralizer shall be first grade quality concentrate diluted with clean
water and applied as surface conditioner of new interior and exterior masonry
walls and other concrete surfaces thus improving paint adhesion and durability.
[5 empty] | • | All exterior concrete surfaces must be finished with elastomeric waterbased
paint, and all interior concrete surfaces must be anti-bacterial, odourless &
stain-resistant elastomeric waterbased paint.
[5 empty] | • | All concrete/masonry surfaces must apply one (1) coat of acrylic concrete
primer and sealer, repair surface imperfections with water based putty, spot
prime puttied areas with acrylic concrete primer and sealer, and two (2) coats of
paint for top coat (acrylic odourless elastomeric paint for exterior and
anti-bacterial, odorless & stain-resistant paint for interor). Allow 2 hours drying
time in between coats.
[5 empty] | • | Metal surfaces must apply one (1) coat of metal primer paint and two (2)
coats of quick drying enamel paint.
[5 empty] | • | Ceiling / Fiber cement surfaces must apply one (1) coat of acrylic concrete
primer and sealer, repair surface imperfections with water based putty, spot
prime puttied areas with acrylic concrete primer and sealer, and two (2) coats of
paint for top coat (acrylic odourless elastomeric paint for exterior and
anti-bacterial, odorless & stain-resistant paint for interor). Allow 2 hours drying
time in between coats.
[5 empty] | • | Use the same brand of paint from start to finish to a good paint body.
[5 empty] | • | Color and pattern shall be specified in the drawings or as approved by the
R2TMC Engineer-in-charge of the Project.
[5 empty] | • | Use the same brand of paint from start to finish to a good paint body.
XI | FENESTRATION WORKS |  | sq.m. | 177.075
| • | Furnishing of Materials, Hardware, Tools, and Labor |  |  | • | Lumber of doors, jambs and panels when required, shall be well-seasoned or
| • | Installation of Doors and Windows |  |  |  | kiln-dried Tanguile wood or equivalent with moisture content of not more
than 14 %.
[5 empty] | • | All doors and window frames shall be in place and rigidly anchored.
[5 empty] | • | Doors and Windows type, sizes, and designs shall conform with the details
indicated in the plan/drawing or otherwise as directed by the R2TMC Engineer-in-
charge of the project.
XII | ROOFING WORKS
(a) | Steel Truss |  | lot | 1
| • | Furnishing of Materials, Labor, and Equipment |  |  | • | All materials and workmanship shall conform to the latest applicable
standards or specifications. All works shall conform to the best practice
prevailing in the various trades.
[5 empty] | • | The contractor shall examine the drawings and shall notify the R2TMC
Engineer-in-charge of the project of any discrepancies he may find before
proceeding with the work or during construction.
[5 empty] | • | Structural steel shall conform to American Society of Testing Materials (ASTM).
Electrodes for welding shall conform to the latest code requirements of the
American Welding Society (AWS).
[5 empty] | • | Surfaces to be welded shall be free from loose scale, slag, rust, grease, paint
and any other foreign material. All butt welds shall be full penetration welds.
[5 empty] | • | Details for steel works shall be based on the issued plans and drawings
(b) | Roofing Sheet |  | l.m. | 450
|  | Furnishing of Materials, Labor, and Equipment |  |  | • | All pre-painted metal sheet and roofing accessories shall be oven baked
painted and overall thickness with protective coats of 0.60mm, true to
profiles indicated on the Plans or otherwise as directed by the R2TMC
Engineer-in-charge of the project.
[5 empty] | • | Pre-painted rolling sheets shall be fabricated from cold rolled galvanized iron
sheets specially tempered steel for extra strength and durability.
[5 empty] | • | Design and color shall be subject to the approval of the R2TMC Engineer-in-
XIII | ELECTRICAL WORKS |  | lot | 1
| General |  |  |  | • | All works shall be done under the direct supervision of an Electrical Engineer
| • | Furnishing of Materials, Labor, and Equipment |  |  |  | and in strict accordance with these specifications and of the methods as
prescribed by the latest edition of the Philippine Electrical Code.
[5 empty] | • | All items not specifically mentioned in the specifications as noted on the
drawing but which are obviously necessary to make a complete working
installation shall be included.
[5 empty] | • | All materials shall be brand new and shall be of the approved type meeting all
the requirements of the Philippine Electrical Code and bearing the Philippine
Standard Agency (PSA) mark unless specified or indicated otherwise.
[5 empty] | • | All materials to be used shall conform to the Bureau of Product Standard (BPS)
Specifications.
[5 empty] | • | Upon completion of the electrical construction work, the contractor shall
provide all test equipment and personnel and to submit written copies of all
test results.
XIV | INSTALLATION OF FIRE SUPPRESSION SYSTEM (INCLUDING ALL CONSUMABLES, TAPPING AND NEEDED SUPPORT) |  | lot | 1
| • | Furnishing of Materials, Labor, and Equipment |  |  | • | All materials and workmanship shall conform to the latest applicable
standards or specifications. All works shall conform to the best practice
prevailing in the various trades.
[5 empty] | • | The contractor shall examine the drawings and shall notify the R2TMC
Engineer-in-charge of the project of any discrepancies he may find before
proceeding with the work or during construction.
[5 empty] | • | All items not specifically mentioned in the specifications as noted on the
drawing but which are obviously necessary to make a complete working
installation shall be included.
[5 empty] | • | Upon completion of the fire suppression system, the contractor shall
provide all test equipment and personnel and to submit written copies of all
test results.
XV | PLUMBING WORKS
| General |  | 1 | lot
| • | Furnishing of Materials, and Labor |  |  | • | All sanitary/plumbing works shall be done under the supervision of a Sanitary
Engineer and in strict accordance with these specifications and of the methods
as prescribed by the latest edition of the Philippine Plumbing Code, Sanitary
Code of the Philippine.
[5 empty] | • | All items not specifically mentioned in the specifications or noted on the
drawings but which are obviously necessary to make a complete working
installation shall be included.
[5 empty] | • | All sewer pipes shall be polyvinyl chloride (PVC) pipes series 1000 “branded”
or approved equal. Fittings shall be PVC conforming to ASTM D1784 and
solvent cement joint materials shall conform to ASTM 2564. Sewer pipe shall
be tested according to Plumbing Code. All testing shall be witnessed by CDC
authorized representative.
[5 empty] | • | All water supply pipes and accessories shall be PPR pipe.
[5 empty] | • | All plumbing fixtures Model make and color shall be submitted for approval
prior to delivery at jobsite by the R2TMC Engineer-in-charge of the construction.
[5 empty] | • | Effluent of the Septic Tank shall be tap to the nearest Pipeline of the Waste
water treatment plan
General Note:
[5 empty] | • | Any discrepancies within the issued drawings/plans and specifications, the
actual site condition and actual construction shall be conferred with the
R2TMC Engineers and no execution of work shall be done without their consent
and final approval.
[5 empty] | • | All materials and workmanship shall conform to the latest applicable
standards or specifications. All works shall conform to the best practice
prevailing in the various trades.
[5 empty] | • | All construction and workmanship shall be subject to inspection, examination
and testing by the R2TMC Engineer-in-charge of the project. The R2TMC Engineer-
in-charge of the project shall have the right to reject defective materials and
workmanship or require its correction.
Name of Company: _________________________________________________
Name of Representative: ____________________________________________
Signature of Representative: _________________________________________
Date: ___________________________________________________________